## CAP
No | Recommendation header | Recommendation Summary | adidas supplementary observations | CAP by Arikbey | CAP deadline | Status update
1 | Establishing an effective social dialogue between Arikbey and the union | Managements of both factories, including their lawyers, are recommended to realize that they are a part of long-time strategic business partner of adidas and bound to follow adidas Workplace Code of Conduct and benchmark requirements on workers’ key rights areas including freedom of association and collective bargaining rights of the workers. Therefore, refusing social dialogue by using the norms of local legislation is unacceptable and both factories should be open to having meetings to discuss any matters related with the members of the union. This is even a more pressing issue for the Arik Bey Beysehir factory where several union members were dismissed and there are at least three ongoing lawsuits about this issue. Investigator recommends Arik Bey management and TEKSIF union to organize a meeting under the supervision of adidas to resolve all pressing issues, including concerning dismissed union members and freedom of association issues reported by the union. | It is not adidas’ practice to directly supervise discussions or negotiations between unions and our suppliers. However, we do actively support and encourage worker-management dialogue, including with union representatives. In the case of Arikbey the union is not a formal bargaining unit and has not secured a membership level to be formally registered as a plant level union. Nevertheless, the union has affiliated members employed in the two factories and an open dialogue is required to address the Freedom of Association issues and worker dismissals referred to in the FLA investigative report. We have requested that Arikbey seeks to openly discuss the allegations and concerns raised by the union and provide a formal note summarizing points of agreement/disagreement from any meeting held between the factory management, the union, and their legal representatives. We need to state unequivocally that any form of discrimination or differential treatment of workers because of their trade union membership is a direct violation of adidas' Workplace Standards. | Being of the oldest manufacturers in our region, we have been working with Adidas for over 30 years without any conflict with our customers or employees. In this framework, we will, as we always have, protect all the constitutional rights of employees as part of our core values and principles in accordance with the Constitution of the Republic of Turkey, the Law no 6356 on Trade Unions and Collective Bargaining Agreement, and we undertake to maintain such impartiality while doing so. To maintain our impartiality, we believe that it is preferable to partake in a dialogue with unions only when a majority is achieved in accordance with the relevant provisions of the law. However, as an institution that is well aware that open and continuous communication with all our workers, whether they are members of any union or not, will only benefit all stakeholders, we will, in addition to our existing communication channels, we will start having regular 'Time to Talk' meetings with our workers to encourage them further to raise their concerns, complaints and suggestions. | October'22 |  | 777-8888
2 | Respecting the right to freely associate | As explained in detail in this report, the owners of these factories are very prominent and influential figures in those districts where the factories are located at, therefore, many other workplaces and even local municipalities are involved into this issue with or without the knowledge and consent of the factory owners. To address such issues in future, the owners of the factories are recommended to share a written declaration that they are respecting the freedom of association and collective bargaining rights of their workers and this declaration should be posted in prominent places in both factories. In addition, it is recommended that owners of the factories to get in touch with the other business owners and local authorities and inform them about not to involve in any matters related with their factories and workers such as dismissing or threatening with dismissal of the relatives of their workers, organizing efforts to block any press briefing of the union and/or harassment of the union officials or the union members. | As it is clearly stated in adidas' Workplace Standards and supporting Employment Guidelines, failure to respect Freedom of Association is a serious violation and a threshold issue, one which may trigger enforcement action. In June 2021 adidas recommended Arikbey to provide an FoA training to all employees to ensure that they were aware of their legal rights and freedom to associate. During adidas' last audit, which was conducted in March'22, it was observed that this training had still not been delivered. In parallel, there had been formal complaints raised about FoA, discrimination and harassment. The need for training and clear communications to the workers on their Freedom of Association and Collective Bargaining rights has becomes even more critical. It is a pending issue which needs to be addressed as soon as possible. Failure to take the recommended corrective action and improve the overall FoA climate in the workplace will result in enforcement action. | Our employee handbook contains all information about the fundamental rights, including freedoms of association. Handbooks are individually handed to all employees during recruitment. In addition, QR code posters are posted so that employees can review it when required. To take employees with no smartphones into account, employee handbook is placed on the home screen of company tablets owned by all operators in the field. In addition, all employees can directly reach the management team through WoVo, worker representation and open letter applications. As of the first week of October an outlet will be created where all employees will be able to reach the management team face-to-face and report their demands directly through monthly "Time to Talk" meetings. In addition, FoA training and correct communication skills trainings will be provided for all line supervisors, middle and senior managers at the end of September through an independent and expert instructor recommended by the SEA team. Likewise, the rights regarding freedom of association and our company's policies and commitments on this matter will also be provided to the employees in the same period by an independent instructor. Since our employees will be trained in small groups in order for the training to be efficient and effective, these trainings are planned to be completed in mid-October | Mid of October'22 |  | 777-8888
3 | Illegal dismissal of employees | It was observed that Arik Bey Beysehir factory has continued recruitment of new workers after the dismissal of union members which shows that there are employment opportunities arising at this factory from time to time. Therefore, it is recommended to factory management to consider the union member workers who were dismissed and signed a settlement with the factory previously, for such job openings. | According to the Turkish labor law, if a worker is not dismissed for a valid reason, the worker needs to be rehired. Or if someone is dismissed due to downsizing, the factory management needs to first recall the dismissed worker when hiring new people. Arikbey dismissed 9 workers in February '22 claiming that this was due to their poor job performance. adidas was notified of these dismissals by the affected workers and by the local trade union, TEKSIF, who alleged that the dismissals were due to trade union membership. adidas immediately commissioned an independent monitor to investigate. We received feedback that there was no compelling evidence to show that these workers had been dismissed due to their union membership, as the membership status was not known to the supplier, but the dismissals had breached the labor law (under the law an employer is not able to dismiss an employee due their performance, unless they have in place an objective performance evaluation system). It was on these grounds that Arikbey was asked by adidas to immediately rehire these workers. However, out of the 9 workers, 6 signed an 'ikale' with the factory (i.e. an official agreement signed before a court for financial compensation in lieu of reinstatement), one was determined to have been legally dismissed (due to their status as a probationary worker), and two workers did not agree to an 'ikale' (i.e. they did not accept the financial package offered by Arikbey). Given legally-binding agreements had been reached with 6 workers, and one was deemed to be lawfully dismissed, SEA recommended that the two remaining workers be rehired. This Arikbey has refused to do, on the grounds of the legal suit taken by TEKSIF. Arikbey is now subject to Enforcement Action until the issue is remedied. Pending issues may lead to further enforcement action. The chosen enforcement action will be proportionate, targeted and transparent as per our published Enforcement Guidelines. | In our 37-year employee-employer relationship, the rights of employees has always been our company’s uttermost priority, and we are committed to maintain this approach. Besides, Arıkbey takes notice of legal reasons prior to any termination of contract. We undergo productive meditation processes with employees and we have reached an agreement in all cases other than the lawsuits subjected to the report. In any case, it is legally not possible for Arıkbey to know when a worker joins a union. In addition, one of the court cases subject to the report and discussion has been already rejected by the Court which also proves that claims of union are not correct and dismissal is legal. And we do expect the remaining two cases to be rejected as well as we are confident that the dismissals have nothing to do with any FoA issue but business needs (they had worked for us for only 4 months which legally does not even require a reason to dismiss a worker). We do respect and do expect all parties to respect the court process and judgment and we hereby would like to repeat that we undertake to abide the judicial decision of these lawsuits. Still, Arikbey continues to be open to constructive dialogue during dismissal case, including direct engagement with affected workers (or their legal representatives) if this helps resolve their concerns. We have immediately stopped dismissing any one for low performance until a proper, fair and objective performance evaluation system is available. In the meantime, Arikbey has recruited no workers with the same duties and responsibilities of the dismissed workers and shows great sensitivity in this regard. Unfortunately, we foresee that we will not be able to employ new employees for above mentioned duties and responsibilities this year due to the global financial crisis. Lastly, we also would like to emphasize that neither Arıkbey nor its shareholders, who are untenderly accused in the report for using personal influence to harass employees, have ever engaged in such actions. We therefor completely disagree with these false and unacceptable claims. We, as a very well establish company and being partner to adidas for more than 30 years in Turkey, do not hold any reservation or concern regarding the union. Our company's respect for and commitment to both local laws and international human rights standards has been clearly emphasized not only in statements, but also in our company policies that have been in effect for many years. | October'22 |  | 777-8888
4 | Providing all workers with a training on freedom of association and collective bargaining | To address the lack of knowledge about basics of freedom of association and collective bargaining rights of the workers, a series of training sessions should be prepared for workers and managerial staff (including supervisors and line chiefs) for both factories. These training sessions should be prepared and delivered by a credible and respected individual selected by adidas SEA team instead of the factory management. Content of the training should cover both local laws and adidas Code/Benchmark requirements. | This is a pending issues which was also recommended by the SEA team. To address complaints about 'not respecting FoA rights' it is recommended that an FoA training is given to all workers and managers by a respected third party. The emphasize of this training should not be only what FoA related rights are but also the commitment of the management to respect these rights. | We will start providing trainings to all of our employees regarding their rights to freedom of association, as well as our company policies and commitments on this matter, by the end of September, by an independent and respected scholar who is well experienced in these kind of trainings. Since our employees will be trained in small groups in order for the training to be efficient and effective, these trainings are planned to be completed by mid-October. | Mid of October'22 |  | 777-8888
5 | Establishing an objective performance evaluation system | Absence of an objective and well-established performance evaluation system in both factories is making personal performance evaluation a highly contested issue. Both factories should establish an objective, clear and understandable system for performance evaluation. Such a system must be established in coordination and with the feedbacks of workers, and all workers should be informed about such a system before it is launched. | Establishing an objective and effective performance evaluation system that is linked with financial incentives and promotions was already a recommendation in the SEA CAPs and Arikbey had activated a system named ‘Solutions’ in October'21 for this. The system is still in its pilot phase. And the plan is that by Jan'23 it is running in full and linked with financial incentives together with seniority, , competencies and skills. It is also recommended that Arikbey does not dismiss anyone for performance reasons till the system proves itself to be functioning properly and 100% on objective criteria. | The production management system called ‘Solutions’ has been active since October 2021, but performance evaluation system is not yet active and will be activated gradually until the end of the year based on collected data. Priority will be given to production operators. An independent evaluation will be achieved according to the data of the performance evaluation system in terms of wage and career management. As you recommended, no employee will be dismissed for performance reasons till the system proves itself. It will be ensured that the system assess employees through a fair and objective evaluation method in which parameters such as compliance with business rules, seniority, competencies and performance are taken into account. We aim to start implementing the new wage system that is linked with 'Solutions' for the incentive and promotions by January 2023. | January'23 |  | 777-8888
6 | Improving wage-setting systems to ensure fair compensation at both factories | As explained in detail in earlier sections of the investigation report, the wage policy of both factories is simply following minimum wage requirements without taking into consideration several other factors such as living wage/fair compensation concepts, seniority, and individual performance of the workers. It is recommended that managements of both factories to work on this issue by getting help from the adidas SEA department | adidas was informed through recent workers interviews and the operational grievance (WOVO) system that the workers do not believe that Arikbey is paying a fair wage. Though Arikbey pays above the LMW on average and compensates workers for their leave and other entitlements properly and promptly, workers believe that the LMW and the pay system is not keeping up with inflation and their cost of living challenges. There is also no clear policy or implementation mechanism in place to ensure the wage system reflects the economic challenges facing employees. We recommend that Arikbey reviews and revises its wage system to make it objective and fair, factoring in the current economic challenges in Turkey. Such a review should consider all relevant operating factors, including business turnover, legal requirements, job responsibilities, overtime, seniority, technical competence and team/individual performance, etc. | Since 2012, we have been following a wage setting system based on HAY group (Korrnfery) - grade methodology. It is alleged that we have a minimum wage level, but we have just 10% workers who receive minimum wage. Highest sewing operator wage is 17.5% higher than minimum wage while the average sewing operator wage is 9% higher. Still, hearing the complaints of our workers and the recommendations of our buyers, we will review our wage system based on economic challenges of the country and purchasing practices of our customers (considering all relevant operating factors, including business turnover, legal requirements, job responsibilities, overtime, seniority, technical competence and team/individual performance, etc.). We will also link the new performance evaluation system for financial incentives to ensure it is all based on objective criteria. We aim to start implementing the new wage system by January 2023. | January'23 |  | 777-8888
7 | Respecting freedom of movement (going to the Mosque for Friday prayers) | Freedom of movement limitations implemented by Arik Bey Beysehir factory since February 2022 should be lifted. Currently, workers are not allowed to leave factory premises during the break hours and for Friday prayers – following the TEKIF union’s press statement in front of the factory building. | As it is clearly stated in adidas' guidelines and policies, restricting the freedom of movement of workers is a threshold issue, which we do not tolerate. Looking back there has been no past complaints or non-compliances raised about this issue and it appears to have been triggered by Arikbey's recent decision to stop supplying buses to transport workers to Friday prayers. Previously there was no masjid in Arikbey, with the closest mosque being located at least 15km away. Having now built an authorized masjid within the premises, Arikbey informed workers that they will cancel bus services on Friday afternoons. There is no legal obligation for Arikbey to provide such a service but it was a benefit enjoyed by the workers. It is therefore recommended that Arikbey strengthen its communication to the workforce and provide documented training on company policies and procedures, which explains freedom of movement and conveys to workers that they are free to leave factory premises during break times if they wish to do so. | As it is also stated in our polices, all of our employees are free to use their rest breaks as they wish in line with the working hours of our company, and they can also use the mosque for praying if they wish to do so. In the last years, we provided free transportation on Fridays from our facility to the mosques in the vicinity as we had no proper masjid (small size mosque). Due to the distance, the workers were not able to start on time and they had almost no time left to have lunch on Fridays, which is why, in collaboration with the official center of religious affairs, we managed to have a proper masjid within our premises and therefore stopped providing transfers to the mosques. This was done to allow workers more time for rest and lunch as well as to ensure that they are able to start work on time after the break. Arikbey’s only expectation is for employees to comply with break times and disciplinary rules. This will also be emphasized during the trainings we will start to give by the end of September – that freedom of movement is a right we have and will always respect, and that they can leave the factory premises if they wish to do so during breaks providing that they comply with the working hours. | End of September'22 |  | 777-8888
8 | Strengthening internal audit mechanism at both factories and providing all workers with refreshing trainings | Although there is a social compliance department in company headquarters in Istanbul and the internal audits are taking place on a periodical basis, the quality and impartiality of those audits are highly contested by workers. Structuring and the reporting line of this department should be evaluated to ensure independence and impartiality. | We recommend that the management compares the findings and recommendations of second- and third-party auditors/monitors to evaluate the performance of the internal compliance team and look for consistency in findings, or any gaps. adidas' inhouse compliance staff will support with additional training, if required. | The performance of our internal compliance department is not only monitored by our management team but also the compliance teams of our customers. Our GM committed to review and evaluate all major and minor findings in all compliance reports and will follow to ensure necessary actions are taken on time and in a sustainable manner. We will ask the compliance teams of our buyers to help us with providing a refresher training to our internal auditing team and we will also start comparing the findings of external audits with the findings in the internal audit reports to compare the quality. | End of October'22 |  | 777-8888
9 | Establishing a voluntary overtime system | According to the survey results, many workers complained about excessive and mandatory overtime (as per the allegations, the factory does not arrange shuttle buses for workers who do not want to stay for overtime) | As clearly stated in our Workplace Standards and Employment Guideline, all supplier partners must operate lawfully. They should not exceed the working hours limits under the law (including cumulative hours) and all overtime must be voluntary. In audits conducted in 2021 we found that Arikbey had exceeded the yearly legal limits (270 hours of OT in a year) and this non-compliance was flagged with Arikbey. During adidas' March '22 commissioned audit, worker interviews revealed that some workers had expressed concerns about "compulsory OT" due to the lack of available transportation home after regular working hours finished. Based on FLA's recent investigations and our own observations we recommend that Arikbey: -Remind all workers, supervisors and managers about its overtime policy, which states that OT work can only be done on voluntary basis and do so during a documented training, -Ensure service vehicles are available after regular working hours, so the option remains available to every single worker to return home, should they opt not to stay for OT working, -Wherever possible reduce OT working hours through better planning and set reasonable and clear production targets which can be met within regular work hours | Voluntary basis OT attitude is clearly stated on employee handbook, orientation training and in our company policies. On top of that we will remind all workers, supervisors and managers about out OT policy requirement through a documented training and this will be completed till end of October. -Shuttles are always available due to 3 shift working. We have been well informed about the exceptional issues which have been seen as compulsory work by our employees and, as before, we will continue to provide shuttle for those who do not stay for OT working after regular working hour -With the support of adidas planning team, order flow management and KPI pressure should be improved. Addition to that, from last March onwards our top management internally decided to balance overtimes to have max 5.5 hours in a week. As of today, our average OT is 2,88 hours per week while allowed legal overtime is 15 hours per week. | End of October'22 |  | 777-8888
10 | Proving non-harassment and abuse trainings for supervisors and managers | Many of the interviewed workers stated that there is verbal abuse by the supervisor due to production pressure (daily target). In addition, they said the union members are intimidated by the mid-level supervisors even though the factory management team of Beybo Seydisehir claimed that the supervisors took their own initiative to do it and warned them verbally on unionization in the factory. | Verbal abuse or other forms of harassment in the workplace is not acceptable and are a threshold issue under adidas' Workplace Standards. In those cases where a supervisor or manager breaches Arikbey anti-harassment policies, warnings should be given in writing and the case passed to the discipline committee to handle. We recommend that all employees (including line managers, supervisors, managers and workers) are provided annual refresher training and that Arikbey use external experts to provide training on critical topics: workers’ rights with respect to freedom of association, code of compliance, company non-harassment, non-retaliation and non-discrimination policies, workplace grievance systems, and effective communication techniques between supervisors, managers and workers to maintain workplace peace. All trainings should be documented and a follow-up assessment should be conducted to ensure that workers understand fully their rights and the company's policies and systems. | Through the WoVo application, suggestion/complaints boxes, phone numbers of compliance team members and our open door policy, each worker can share all their complaints whenever they want either anonymously or by noting their name. In addition to these grievance channels, there is also a MOOD feature on the shop floor tablets which aims is to follow our workers' daily mood and if they are sad we can investigate immediately the root cause. We will provide refresher trainings about the objectivity and confidentiality of these tools and that every complaint/suggestion raised to the attention of the management team is handled seriously, timely and confidentially. We will also schedule trainings on adidas Workplace Standards, the workers’ rights on freedom of association, company non-harassment, non-retaliation and non-discrimination policies, workplace grievance systems, and effective communication techniques between supervisors, managers and workers to maintain workplace peace. These trainings will be given by an experienced and respected scholar. According to ISO standards we measure efficiency of the training as a must. | Mid of October'22 |  | 777-8888
11 | respecting freedom of movement (restrictions on using the restrooms) | During the interviews and surveys (see relevant sections of the TPI report for details), some of the workers complained saying that there is limitations on restroom use during working hours | All workers must have full and unlimited access to restrooms. If this is not the practice but the workers feel so, than this must be announced again during the upcoming trainings on company policies and procedures. It must also be clearly posted on the notice boards. All training should be documented and a follow-up assessment conducted to ensure that workers understand their rights and freedoms, including access to the restrooms during working hours. | There is no restriction on using the restrooms. This is also clearly stated in our policies. However looking at the feedback the investrogator received from the workers during the interviews, it looks like not all workers know this. We will provide a training to all employees and managers to make sure that all are reminded about our policy that workers can use the restrooms whenever they need to do so and that they do not need to ask for permission but just inform their line manager that they are going for it so that the line manager knows where s/he is incase it is needed. | September'22 |  | 777-8888
12 | Improving the quality of corrective action plans | Investigator found some of Arik Bey Beysehir management’s response to the corrective action plan (CAP) shared by adidas to be insufficient and not solution oriented - see relevant section of the report for details. Considering the fact that this factory is a part of long-time adidas strategic supplier, it is expected that the factory’s remediation plan should be time bounded, and solution oriented. | Arikbey’s compliance team is experienced in creating proper CAPs and following up on the remediation/implementation phase. However, as per the independent auditors recommendations, greater attention should be given to ensuring sustainable solutions for identified gaps and issues, especially those related to the recent FoA complaints. We recommend that Arikbey’s compliance team provides a comprehensive remediation plan based on FLA’s Independent Investigation Report and adidas' related CAP to ensure that remediation phase can start asap and issues can be addressed in a sustainable and timely manner. | We will make sure that the compliance team is empowered enough to ensure comprehensive and compliant remediation plans are provided. A proper remediation plan will be prepared for each recommendation in the FLA TPI report as well the open issues in brands' audit reports within September'22 and the remediation phase will be monitored closely by the management team to ensure issues are closed in a timely and sustainable manner. | September'22 |  | 777-8888